## Slide 1
Ads
SYYAIM SAFEG AI
Google Ads
Setup Guide
+ 30-Day Action Plan
Step-by-Step
Account Setup
Campaign
Architecture
Keyword
Targeting
30-Day
Action Plan

## Slide 2
OVERVIEW
Your Google Ads Journey — 5 Phases to Launch
1
🔧
Account Setup
Day 1–2
›
2
🏗️
Campaign Build
Day 3–5
›
3
🎯
Keywords & Ads
Day 5–7
›
4
🚀
Tracking & Launch
Day 7–8
›
5
📈
Optimise & Scale
Day 9–30
EXPECTED RESULTS BY DAY 30
15–20
Demo bookings
₹120–220
CPC safety keywords
6–10%
Target CTR
<₹40K
Monthly budget
3–5 days
To first lead
Syyaim SafeG AI · Google Ads Launch Guide

## Slide 3
PHASE 1 · ACCOUNT SETUP
Create & Configure Your Google Ads Account — Day 1
1
Create Google Ads Account
Go to ads.google.com → Click 'Start Now'
Sign in with your business Google account
Select 'Switch to Expert Mode' — CRITICAL (avoids Smart campaigns)
Choose campaign goal: 'Create an account without a campaign'
Set billing country: India · Currency: INR (₹)
2
Business Information
Business name: Syyaim SafeG AI
Website URL: syyaimsafeg.ai
Time zone: India Standard Time (IST, +5:30)
Auto-tagging: Enable (required for GA4 tracking)
Industry: Technology → Software
3
Billing Setup
Payment method: Credit card or bank transfer
Billing threshold: Start at ₹500 (auto-increases)
Monthly invoice: Apply once spend > ₹50K/mo
Enable payment notifications for budget alerts
Save GST number for Input Tax Credit
4
Account Structure
Create 1 Manager Account (MCC) if agency-managed
Link Google Analytics 4 property immediately
Enable Google Merchant Centre (future use)
Set up Google Tag Manager container
Grant access: Admin → your team
Syyaim SafeG AI · Google Ads Launch Guide

## Slide 4
PHASE 1 · ACCOUNT SETUP
Link Analytics & Configure Settings — Day 2
5
Link Google Analytics 4
GA4 → Admin → Google Ads Links → Link
Import GA4 goals as Ads conversions
Enable auto-tagging in Ads account
Verify UTM parameters firing in GA4 Realtime
Set attribution model: Data-driven (or Last click)
6
Install Conversion Tracking
Install Google Ads tag via Google Tag Manager
Create conversion: 'Demo Form Submit' → value ₹60,000
Create conversion: 'Pricing Page 30s+' → micro conversion
Create conversion: 'ROI Calculator Used'
Test with Tag Assistant Chrome extension
7
Set Account Preferences
Language targeting: English + Hindi
Ad rotation: Optimise (Google picks best ads)
Frequency capping: 3 impressions/user/day (Display)
IP exclusions: Add your own office IP
Enable Search Partners (MSN, YouTube search)
8
Remarketing Setup
Create audience: 'All Website Visitors — 30 days'
Create audience: 'Pricing Page Visitors — 14 days'
Create audience: 'ROI Calculator — 30 days'
Create audience: 'Demo Bounced < 30s — 7 days'
Minimum audience size: 100 (Display), 1,000 (Search)
Syyaim SafeG AI · Google Ads Launch Guide

## Slide 5
PHASE 2 · CAMPAIGN BUILD
Campaign Architecture — How to Structure Your Ads
ACCOUNT
Syyaim SafeG AI — India
▼
CAMPAIGNS
Campaign 1
Search — HSE Managers
Campaign 2
Search — Plant Owners
Campaign 3
Display + Remarketing
BUDGET
₹15K/mo · ₹500/day avg
₹15K/mo · ₹500/day avg
₹10K/mo · ₹330/day avg
AD GROUPS (each campaign)
Core Safety KW
Competitor Switch
Compliance KW
ROI / Cost KW
Industry Vertical
AI Technology
💰 Total Month 1 Budget: ₹40,000 · Est. 180–250 clicks · Target 15–20 demo bookings · Expected CPL: ₹2,000–2,600
Syyaim SafeG AI · Google Ads Launch Guide

## Slide 6
PHASE 3 · KEYWORDS & ADS
Upload Keywords — Match Types Explained
KEYWORD MATCH TYPES — CHOOSE CORRECTLY
=
[Exact]
["factory safety system India"]
Highest intent — Use for top 5 proven keywords. Most precise, higher CPC.
~
Phrase
"AI safety monitoring India"
Good balance — Ads show when query contains this phrase in order. Use for most keywords.
?
Broad
factory safety AI
Widest reach — Only for low-CPC discovery. Add negatives daily. Review search terms weekly.
🚫 CRITICAL — Add These Negative Keywords BEFORE Launch:
free · training · jobs · salary · definition · pdf · ppt · download · how to · what is · news · certification · DIY · wikipedia · template · manual · course · study
HOW TO UPLOAD KEYWORDS IN GOOGLE ADS
1
Select Campaign → Click Ad Group → Keywords tab → '+' button
2
Paste keywords one per line in correct match type format: [exact], "phrase", broad
3
Set default Max CPC bid: ₹150 (Exact), ₹120 (Phrase), ₹80 (Broad)
4
Add negatives: Campaign level → Negative Keywords → add full list
5
Check: Keyword Planner → verify search volumes before final upload
Syyaim SafeG AI · Google Ads Launch Guide

## Slide 7
PHASE 3 · WRITE YOUR ADS
Responsive Search Ads (RSA) — Step-by-Step Creation
HOW TO CREATE AN RSA
1
Navigate
Ads & Assets → Ads → + New Ad → Responsive Search Ad
2
Final URL
Link to the audience-specific landing page:
Variant A → /roi-calculator
Variant B → /plant-owners
Variant C → /compliance
3
Display Path
Use: syyaimsafeg.ai/factory-safety/india
(Two optional path fields — fill both)
4
Headlines ×15
Enter all 15 headlines. Mix formats:
5× problem-focused · 5× solution · 5× CTA
Pin Headline 1 = your strongest (₹11 Lakh hook)
5
Descriptions ×4
Write 4 descriptions (90 chars each).
Pin Description 1 = social proof or urgency.
Google will auto-test all combinations.
6
Ad Strength
Aim for "Excellent" strength rating before saving.
Check: Unique headlines, diverse topics, no repetition.
Ad Preview
Sponsored
syyaimsafeg.ai › factory-safety › india
Stop Accidents Before They Happen | AI Safety — ₹2,500/Cam/Mo
Syyaim SafeG AI monitors 16 cameras 24/7, detecting PPE violations
and hazards in <30 seconds. Factories Act compliant. Free 4-week pilot.
Free 4-Week Pilot | PPE Compliance | ROI Calculator | Book Demo
✓ AD QUALITY TIPS
Include top keyword in at least 3 headlines
Use numbers: ₹11 Lakh · 40% · 30 seconds · 6 months
End 2 headlines with a CTA: 'Book Free Demo →'
Each description must be < 90 characters
Add all 4 sitelink extensions before going live
Add callout extensions: '24/7 Monitoring' · 'India Data'
Syyaim SafeG AI · Google Ads Launch Guide

## Slide 8
PHASE 3 · AD EXTENSIONS
Add All Extensions — Increases CTR by 10–15%
🔗
Sitelinks (4 required)
Free 4-Week Pilot → /pilot
Calculate Your ROI → /roi-calculator
Pricing & Plans → /pricing
Book a Demo → /book-demo
📣
Callouts (6 minimum)
24/7 AI Monitoring
Factories Act Compliant
India Data Servers
Works With Existing Cameras
Free Setup Included
📋
Structured Snippets
Header: Services
Values: PPE Detection · Hazard Zone Alerts · Incident Logging · Auto Compliance Reports · Real-Time Dashboard
📞
Call Extension
Add business phone number
Set schedule: Mon–Fri 9am–7pm IST
Enable call reporting in Ads
Set conversion: calls > 60 seconds
Mobile bid adjustment: +30%
📝
Lead Form Extension
Headline: 'Book Free Safety Demo'
Description: Setup in 2 hours, no commitment
Ask: Name · Company · Phone · City
Webhook to your CRM / email
Deliver lead notification instantly
🖼️
Image Extensions
Upload 4 shopfloor safety images
Square (1:1) and landscape (1.91:1)
Show AI detection overlay screenshots
Dashboard screenshot with 97% PPE metric
Avoid logos-only images — show product in use
Syyaim SafeG AI · Google Ads Launch Guide

## Slide 9
PHASE 4 · PRE-LAUNCH CHECKLIST
Don't Go Live Until Every Box Is Ticked — Day 7–8
✓ Tracking
✓
Conversion tag fires on demo form submit
✓
GA4 goals imported into Google Ads
✓
Enhanced conversions enabled
✓
UTM parameters on all landing page URLs
✓ Campaign
✓
3 campaigns created with correct budgets
✓
All 6 ad groups have 15+ keywords each
✓
Negative keyword list added (50+ terms)
✓
Ad rotation: Optimise
✓ Ads
✓
3 RSA variants in each ad group
✓
Ad strength: Excellent or Good
✓
All 6 extension types added
✓
Final URLs work — 200 status, no redirects
✓ Targeting
✓
Geo: 8 priority cities + state targeting
✓
Device bid adjustments set
✓
Ad schedule: Mon–Fri 9am–10pm
✓
Audience observations added (not targeting)
✓ Budget
✓
Daily budgets set for all campaigns
✓
Billing method confirmed — card charged
✓
Budget alerts: 80% + 100% emails set
✓
Shared budget NOT used (keep separate)
✓ Landing
✓
Page load speed < 3s on mobile
✓
Form works and sends email notification
✓
Thank you page fires conversion tag
✓
Page headline matches ad headline
Syyaim SafeG AI · Google Ads Launch Guide

## Slide 10
30-DAY ACTION PLAN
Week 1 — Foundation & Launch (Days 1–7)
Day 1
Create Google Ads account in Expert Mode
Set billing: INR · credit card · GST number
Create Manager Account (MCC)
Link Google Analytics 4 · enable auto-tagging
Install Google Tag Manager on website
Day 2
Set up conversion tracking (3 conversions)
Create remarketing audiences (4 lists)
Verify Tag Assistant shows conversions firing
Configure account preferences (language, IP exclusions)
Add billing alerts at ₹20K and ₹35K
Day 3
Create Campaign 1: HSE Manager Search
Build 6 ad groups with keyword themes
Upload 50 keywords in correct match types
Add all 50+ negative keywords
Set bids: ₹150 exact · ₹120 phrase · ₹80 broad
Day 4
Create Campaign 2: Plant Owner Search
Write 3 RSA variants per ad group
Add all 6 extension types to both campaigns
Set geo targeting: 8 cities + state layer
Create Display Campaign 3 (remarketing only)
Day 5
QA all ads — check URLs, grammar, char counts
Test all landing pages on mobile + desktop
Verify ad strength: all Excellent or Good
Peer-review copy with team
Final keyword review vs. Keyword Planner volumes
Day 6
Set final daily budgets (₹500+₹500+₹330)
Enable Enhanced CPC bidding (not Smart Bidding yet)
Double-check negative keyword lists
Submit ads for review (takes 1–2 business days)
Prepare weekly reporting dashboard in Google Looker
Day 7
🚀 LAUNCH — Enable all campaigns
Monitor first 2 hours for any disapprovals
Check Search Terms report immediately
Add any new negatives from initial data
Send internal launch notification to sales team
Syyaim SafeG AI · Google Ads Launch Guide

## Slide 11
30-DAY ACTION PLAN
Weeks 2–4 — Optimise · Scale · Convert (Days 8–30)
Week 2 (Days 8–14)
Data-driven optimisation
Day 8: Review Search Terms — add 15+ new negatives from real search data
Day 9: Identify top 3 performing keywords — increase bids by 20%
Day 10: Pause any keywords with CTR < 1% after 50+ impressions
Day 11: A/B test landing pages — swap ROI Calculator with calculator widget
Day 12: Check Quality Scores — anything < 5 needs ad copy or landing page fix
Day 13: Add 10 new long-tail keywords from Search Terms report
Day 14: Week 2 report — CTR, CPC, conversions, top search terms
Week 3 (Days 15–21)
Audience refinement & bidding
Day 15: Switch to Target CPA bidding IF you have 15+ conversions (else wait)
Day 16: Review audience observation data — increase bids for best-performing segments
Day 17: Create RLSA (Remarketing Lists for Search Ads) campaigns for pricing page visitors
Day 18: Check device data — mobile vs. desktop CTR. Adjust device bid modifiers ±20%
Day 19: Review ad variation performance — pause headline combinations with < 0.5% CTR
Day 20: Add Customer Match list from your CRM database (min 1,000 emails)
Day 21: Week 3 report — conversion rate, CPL trends, top-performing ad copy
Week 4 (Days 22–30)
Scale what's working
Day 22: Increase budget by 25% on campaigns hitting target CPL
Day 23: Launch Competitor Keyword campaign (Wobot AI, Intenseye alternatives)
Day 24: Create a YouTube bumper ad (6s) using MotionGraphics video clip
Day 25: Review geographic data — add +20% bid adjustments for top-converting cities
Day 26: Request Display Network placements for manufacturing/EHS websites
Day 27: Build 'Demo Attended — Didn't Convert' remarketing audience
Day 28–30: Full month review — build Month 2 plan with data-backed budget allocation
Syyaim SafeG AI · Google Ads Launch Guide

## Slide 12
PERFORMANCE TRACKING
KPIs to Monitor Daily, Weekly & Monthly
DAILY (5 min check)
Budget consumed
< Daily budget
Impressions
> 200/day
Click-through
> 10 clicks/day
Disapprovals
= 0
New search terms
Add negatives
WEEKLY (30 min review)
CTR
Target: 6–10%
CPC
Target: ₹120–220
Conversions
Target: 3–5/week
Quality Score
Target: 7+ avg
Impression Share
Target: > 40%
MONTHLY (Deep analysis)
Total demo bookings
Target: 15–20
Cost Per Lead (CPL)
Target: ₹2,000–3,000
Conversion Rate
Target: 5–8%
Return on Ad Spend
Target: 15× ROAS
Top keyword by conv.
Scale budget 25%
RECOMMENDED REPORTING TOOLS
Google Ads Dashboard (daily)
Looker Studio (weekly report)
GA4 Funnel Exploration (conversion path)
Google Ads Editor (bulk changes)
Syyaim SafeG AI · Google Ads Launch Guide

## Slide 13
TROUBLESHOOTING + NEXT STEPS
Common Problems & Solutions — Then Launch!
📉
Low impressions (<100/day)
Increase max CPC bids by 30%. Broaden match types. Check campaign status.
👁️
Low CTR (<3%)
Rewrite headlines — lead with ₹11 Lakh hook. Add FOMO element. Test new sitelinks.
💸
High CPC (>₹300)
Add more exact match keywords. Remove broad keywords. Improve Quality Score.
📋
Low conversions (<1%)
Landing page audit: speed test, form visibility, CTA above fold. Add trust signals.
🚫
Ad disapprovals
Check: No superlatives (Best/#1). No excessive caps. Prices must be accurate.
⏰
Budget depletes by noon
Enable ad scheduling: full spend over 8am–9pm. Or increase daily budget by 30%.
🚀 Ready to Launch?
Follow this guide top-to-bottom · Allow 2–3 days for ad approval · Expect first leads within 5–7 days of launch
For questions → marketing@syyaimsafeg.ai · syyaimsafeg.ai
Syyaim SafeG AI · Google Ads Launch Guide